## Slide 1: RIPE Database Requirements Task Force
DBTF | RIPE 83

## Slide 2: Task Force Members
Nick Hilliard
James Kennedy (co-Chair)
Shane Kerr (Vice Chair)
Peter Koch
Sara Marcolla (until February 2021)
Bijal Sanghani (Chair)
DBTF | RIPE 83
RIPE NCC Support:
Boris Duval
Maria Stafyla
Edward Shryane

## Slide 3: RIPE Database Requirements Task Force
The RIPE Database Requirements Task Force was formed in October 2019 as an outcome of the Big Picture BoF that took place at RIPE 78 in Reykjavik, Iceland.
The Task Force was tasked to produce a RIPE document listing the requirements for the RIPE Database and their rationales.
The Task Force published its final report in October 2021.
DBTF | RIPE | 5 May 2021

## Slide 4: Our Work
Regular meetings (minutes publicly available)
Two surveys
Mailing lists feedback (ripe-list, db-wg)
Three BoFs (May 2020, Oct 2020, May 2021)
Updates at RIPE Meetings (RIPE 80, RIPE 81, RIPE 82)
Data and information collection with support from the RIPE NCC
Three draft published (May 2020, Oct 2020, July 2021)
Final report (October 2021)
DBTF | RIPE 83

## Slide 5: Obstacles
COVID-19 disrupted our working process (no face-to-face meetings, Zoom fatigue etc.)
The scope of the document was large and ambitious
Diverging community views on key topics (e.g. legal address)
Technical topics - hard to steer away from implementation details
DBTF | RIPE | 5 May 2021

## Slide 6: What Went Well
Different backgrounds and expertise
Synergy between task force members
Helpful feedback from the community via the surveys, BoF and mailing lists
Strong support from the RIPE NCC (legal, technical and administrative)
DBTF | RIPE | 5 May 2021

## Slide 7: Principles and Purposes
Data Management Principles
  Data accuracy
  Data consistency
  Data minimisation
  Data security
RIPE Database Purposes
  Providing authoritative and accurate registration of Internet number resources
  Provisioning the Reverse Domain Name System (rDNS)
  Publishing routing policies by network operators (RIPE IRR)
  Facilitating Internet operations and coordination
  Enabling research on and analysis of IP networking in the RIPE region
DBTF | RIPE 83

## Slide 8: Requirements and Other Considerations
Each requirement has a rationale, recommendation and is attached to a purpose
Topics that were considered but not retained as requirements are listed under “other consideration”
The recommendations are only suggestions
They will need to be discussed by the relevant Working Groups before being implemented
DBTF | RIPE 83

## Slide 9: Requirements and Other Considerations
  6.1.1 Baseline requirements for registration information of Internet number resources | database
  6.1.2 IPv4 PA assignments | address policy
  6.1.3 Discourage using the RIPE Database as an IPAM solution | database
  6.1.4 Historical data and personal data filtering | database
  6.3.1 Routing information |routing
  6.3.2 Maintaining accurate routing origin information | routing
  6.3.3 RPSL | routing
  6.3.4 RPKI Database | routing and database
  6.4.1 Operational Contact Information (PERSON and ROLE Objects) | database
  6.4.2 Publishing the legal address of resource holders | database and cooperation
DBTF | RIPE 83

## Slide 10: Up Next
The RIPE Chair Team will coordinate with the relevant WGs
WGs to discuss the recommendations via their respective mailing lists
If accepted, the RIPE NCC to implement the recommendations
DBTF | RIPE 83